## Project Timeline
Data Platform Project Timeline ( FY 25- 28 )
|  |  | FY 25 | [5 empty] | FY 26 | [11 empty] | FY 27
|  |  | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01
Overall | 1. Design and provision data platform environment | 1 | bar: 2025-01-01 to 2025-05-01
| 2. Design journals criteria, payroll SAR model and end to end automation | 4 | bar: 2025-07-01 to 2025-12-01
| 3. Mapping and supplementary datasets | 2 | bar: 2025-08-01 to 2026-12-01
| 4. Design risk assessment dashboards for journals and payroll | 4 | bar: 2025-01-01 to 2025-11-01
| 5. Establish and finalise access provisioning and review process | 5 | bar: 2025-10-01 to 2026-02-01
| 6. Usage monitoring and reporting | 5 | bar: 2026-01-01 to 2026-02-01
| 7. Develop business process documentation and UAT test plan | 5 | bar: 2025-11-01 to 2026-02-01
Gov Connect | 1. Onboarding, Environment Setup & Configuration | to Feb 2025 | bar: 2025-01-01 to 2025-02-01
1. Design and Provisioning data platform environment | bar: 2025-01-01 to 2025-02-01
2. Data Transfer Environment | bar: 2025-01-01 to 2025-02-01
3. Staging and Source Data Storage | bar: 2025-01-01 to 2025-02-01
4. Data Models in Snowflake | bar: 2025-01-01 to 2025-02-01
5. Data lake Storage Layers | bar: 2025-01-01 to 2025-02-01
6. Data lake storage Secure Containers | bar: 2025-01-01 to 2025-02-01
7. Data Transfer Scripts | bar: 2025-01-01 to 2025-02-01
8. Access Security Groups | bar: 2025-01-01 to 2025-02-01
| 2. Data and Business Rules Design | to Feb 2025 | bar: 2025-01-01 to 2025-02-01
1. Design and Test Business Rules | bar: 2025-01-01
2. Data Models and Storage | bar: 2025-01-01
3. Data Specification and Development | bar: 2025-01-01
4. Data Loading and Validation | bar: 2025-02-01
5. Business Rules and Backfill Logic | bar: 2025-02-01
6. Mapping and Supplementary Datasets | bar: 2025-02-01
| 3. Data Processing & Transformation | to April 2025 (DS 1, 4 & 5) and October 2025 (DS 2 & 3) | bar: 2025-02-01 to 2025-03-01; 2025-09-01 to 2025-11-01
1. Ingestion Pipeline | bar: 2025-02-01; 2025-09-01
2. Error Handling and Logging | bar: 2025-02-01; 2025-09-01
3. Monitoring Alerts | bar: 2025-02-01; 2025-09-01
4. Data Cleansing | bar: 2025-02-01; 2025-09-01
5. Transformation Logic | bar: 2025-02-01 to 2025-03-01; 2025-09-01 to 2025-10-01
6. Reconciliation Logic | bar: 2025-02-01 to 2025-03-01; 2025-09-01 to 2025-10-01
7. Data Quality Exception Monitoring | bar: 2025-03-01; 2025-10-01
8. Quarterly Data Load and Verification | bar: 2025-03-01; 2025-10-01
9. Cross-client Dataset Mapping and Testing | bar: 2025-03-01; 2025-10-01
| 4. Automation, Testing & Deployment | Up to November 2025 | bar: 2025-09-01 to 2026-02-01
1. Journals Criteria and Workpapers | bar: 2025-09-01 to 2025-10-01
2. Automated Routing of Workpapers | bar: 2025-10-01
3. Automated Scripts for Audit and Testing | bar: 2025-10-01 to 2025-11-01
4. Risk Assessment Dashboards | bar: 2025-11-01
5. Refactoring Design | bar: 2025-11-01
| 5. Training & Process Documentation | Between January 2026 to February 2026 | bar: 2026-01-01 to 2026-02-01
1. Documentation and Access Provisioning | bar: 2026-01-01
2. Training and Information Sessions | bar: 2026-02-01
3. Feedback and Refinements | bar: 2026-02-01
4. Usage Monitoring and Reporting | bar: 2026-02-01
5. Develop Business Process Documentation
MyWorkZone | 1. Onboarding, Environment Setup & Configuration | July 2025 to February 2026 | bar: 2025-07-01 to 2026-03-01
1. Design and Provisioning data platform environment | bar: 2025-09-01 to 2025-11-01
2. Data Transfer Environment | bar: 2025-10-01 to 2025-12-01
3. Staging and Source Data Storage | bar: 2025-12-01 to 2026-01-01
4. Data Models in Snowflake | bar: 2026-01-01
5. Data lake Storage Layers | bar: 2026-01-01 to 2026-02-01
6. Data lake storage Secure Containers | bar: 2026-02-01 to 2026-03-01
7. Data Transfer Scripts | bar: 2026-03-01
8. Access Security Groups | bar: 2026-03-01
| 2. Data and Business Rules Design | August 2026 to June 2026 | bar: 2025-08-01 to 2026-06-01
1. Design and Test Business Rules | bar: 2025-11-01 to 2026-02-01
2. Data Models and Storage | bar: 2025-12-01 to 2026-03-01
| 3. Data Specification and Development | August 2025 to June 2026 | bar: 2025-08-01 to 2026-06-01
4. Data Loading and Validation | bar: 2026-01-01 to 2026-04-01
5. Business Rules and Backfill Logic | bar: 2026-02-01 to 2026-05-01
6. Mapping and Supplementary Datasets | bar: 2026-03-01 to 2026-06-01
| 3. Data Processing & Transformation | March 2026 to June 2026 | bar: 2026-03-01 to 2026-06-01
1. Ingestion Pipeline | bar: 2026-03-01 to 2026-04-01
2. Error Handling and Logging | bar: 2026-03-01 to 2026-04-01
3. Monitoring Alerts | bar: 2026-03-01 to 2026-04-01
4. Data Cleansing | bar: 2026-04-01 to 2026-05-01
5. Transformation Logic | bar: 2026-04-01 to 2026-05-01
6. Reconciliation Logic | bar: 2026-05-01 to 2026-06-01
7. Data Quality Exception Monitoring | bar: 2026-05-01 to 2026-06-01
8. Quarterly Data Load and Verification | bar: 2026-06-01
9. Cross-client Dataset Mapping and Testing | bar: 2026-06-01
| 4. Automation, Testing & Deployment | June 2026 to July 2026 | bar: 2026-06-01 to 2026-07-01
1. Journals Criteria and Workpapers | bar: 2026-06-01
2. Automated Routing of Workpapers | bar: 2026-06-01
3. Automated Scripts for Audit and Testing | bar: 2026-06-01
4. Risk Assessment Dashboards | bar: 2026-06-01
5. Refactoring Design | bar: 2026-07-01
| 5. Training & Process Documentation | 2026-07-01 | bar: 2026-07-01
1. Documentation and Access Provisioning | bar: 2026-07-01
2. Training and Information Sessions | bar: 2026-07-01
3. Feedback and Refinements | bar: 2026-07-01
4. Usage Monitoring and Reporting | bar: 2026-07-01
5. Develop Business Process Documentation | bar: 2026-07-01
Health | 1. Onboarding, Environment Setup & Configuration | Same, but push out 6 months compared to MWZ | bar: 2026-01-01 to 2026-09-01
1. Design and Provisioning data platform environment | bar: 2026-03-01 to 2026-05-01
2. Data Transfer Environment | bar: 2026-04-01 to 2026-06-01
3. Staging and Source Data Storage | bar: 2026-06-01 to 2026-07-01
4. Data Models in Snowflake | bar: 2026-07-01
5. Data lake Storage Layers | bar: 2026-07-01 to 2026-08-01
6. Data lake storage Secure Containers | bar: 2026-08-01 to 2026-09-01
7. Data Transfer Scripts | bar: 2026-09-01
8. Access Security Groups | bar: 2026-09-01
2. Data and Business Rules Design | bar: 2026-02-01 to 2026-12-01
1. Design and Test Business Rules | bar: 2026-05-01 to 2026-08-01
2. Data Models and Storage | bar: 2026-06-01 to 2026-09-01
3. Data Specification and Development | bar: 2026-02-01 to 2026-12-01
4. Data Loading and Validation | bar: 2026-07-01 to 2026-10-01
5. Business Rules and Backfill Logic | bar: 2026-08-01 to 2026-11-01
6. Mapping and Supplementary Datasets | bar: 2026-09-01 to 2026-12-01
3. Data Processing & Transformation | bar: 2026-09-01 to 2026-12-01
1. Ingestion Pipeline | bar: 2026-09-01 to 2026-10-01
2. Error Handling and Logging | bar: 2026-09-01 to 2026-10-01
3. Monitoring Alerts | bar: 2026-09-01 to 2026-10-01
4. Data Cleansing | bar: 2026-10-01 to 2026-11-01
5. Transformation Logic | bar: 2026-10-01 to 2026-11-01
6. Reconciliation Logic | bar: 2026-11-01 to 2026-12-01
7. Data Quality Exception Monitoring | bar: 2026-11-01 to 2026-12-01
8. Quarterly Data Load and Verification | bar: 2026-12-01
9. Cross-client Dataset Mapping and Testing | bar: 2026-12-01
4. Automation, Testing & Deployment | bar: 2026-12-01 to 2027-01-01
1. Journals Criteria and Workpapers | bar: 2026-12-01
2. Automated Routing of Workpapers | bar: 2026-12-01
3. Automated Scripts for Audit and Testing | bar: 2026-12-01
4. Risk Assessment Dashboards | bar: 2026-12-01
5. Refactoring Design | bar: 2027-01-01
5. Training & Process Documentation | bar: 2027-01-01
1. Documentation and Access Provisioning | bar: 2027-01-01
2. Training and Information Sessions | bar: 2027-01-01
3. Feedback and Refinements | bar: 2027-01-01
4. Usage Monitoring and Reporting | bar: 2027-01-01
5. Develop Business Process Documentation
Transport | 1. Onboarding, Environment Setup & Configuration | Same as MWZ (how is impacted by internal transport project?) | bar: 2025-07-01 to 2026-03-01
1. Design and Provisioning data platform environment | bar: 2025-09-01 to 2025-11-01
2. Data Transfer Environment | bar: 2025-10-01 to 2025-12-01
3. Staging and Source Data Storage | bar: 2025-12-01 to 2026-01-01
4. Data Models in Snowflake | bar: 2026-01-01
5. Data lake Storage Layers | bar: 2026-01-01 to 2026-02-01
6. Data lake storage Secure Containers | bar: 2026-02-01 to 2026-03-01
7. Data Transfer Scripts | bar: 2026-03-01
8. Access Security Groups | bar: 2026-03-01
2. Data and Business Rules Design | bar: 2025-08-01 to 2026-06-01
1. Design and Test Business Rules | bar: 2025-11-01 to 2026-02-01
2. Data Models and Storage | bar: 2025-12-01 to 2026-03-01
3. Data Specification and Development | bar: 2025-08-01 to 2026-06-01
4. Data Loading and Validation | bar: 2026-01-01 to 2026-04-01
5. Business Rules and Backfill Logic | bar: 2026-02-01 to 2026-05-01
6. Mapping and Supplementary Datasets | bar: 2026-03-01 to 2026-06-01
3. Data Processing & Transformation | bar: 2026-03-01 to 2026-06-01
1. Ingestion Pipeline | bar: 2026-03-01 to 2026-04-01
2. Error Handling and Logging | bar: 2026-03-01 to 2026-04-01
3. Monitoring Alerts | bar: 2026-03-01 to 2026-04-01
4. Data Cleansing | bar: 2026-04-01 to 2026-05-01
5. Transformation Logic | bar: 2026-04-01 to 2026-05-01
6. Reconciliation Logic | bar: 2026-05-01 to 2026-06-01
7. Data Quality Exception Monitoring | bar: 2026-05-01 to 2026-06-01
8. Quarterly Data Load and Verification | bar: 2026-06-01
9. Cross-client Dataset Mapping and Testing | bar: 2026-06-01
4. Automation, Testing & Deployment | bar: 2026-06-01 to 2026-07-01
1. Journals Criteria and Workpapers | bar: 2026-06-01
2. Automated Routing of Workpapers | bar: 2026-06-01
3. Automated Scripts for Audit and Testing | bar: 2026-06-01
4. Risk Assessment Dashboards | bar: 2026-06-01
5. Refactoring Design | bar: 2026-07-01
5. Training & Process Documentation | bar: 2026-07-01
1. Documentation and Access Provisioning | bar: 2026-07-01
2. Training and Information Sessions | bar: 2026-07-01
3. Feedback and Refinements | bar: 2026-07-01
4. Usage Monitoring and Reporting | bar: 2026-07-01
5. Develop Business Process Documentation
Education | 1. Onboarding, Environment Setup & Configuration | Same as MWZ, but push out by 3 months | bar: 2025-10-01 to 2026-06-01
1. Design and Provisioning data platform environment | bar: 2025-12-01 to 2026-02-01
2. Data Transfer Environment | bar: 2026-01-01 to 2026-03-01
3. Staging and Source Data Storage | bar: 2026-03-01 to 2026-04-01
4. Data Models in Snowflake | bar: 2026-04-01
5. Data lake Storage Layers | bar: 2026-04-01 to 2026-05-01
6. Data lake storage Secure Containers | bar: 2026-05-01 to 2026-06-01
7. Data Transfer Scripts | bar: 2026-06-01
8. Access Security Groups | bar: 2026-06-01
2. Data and Business Rules Design | bar: 2025-11-01 to 2026-09-01
1. Design and Test Business Rules | bar: 2026-02-01 to 2026-05-01
2. Data Models and Storage | bar: 2026-03-01 to 2026-06-01
3. Data Specification and Development | bar: 2025-11-01 to 2026-09-01
4. Data Loading and Validation | bar: 2026-04-01 to 2026-07-01
5. Business Rules and Backfill Logic | bar: 2026-05-01 to 2026-08-01
6. Mapping and Supplementary Datasets | bar: 2026-06-01 to 2026-09-01
3. Data Processing & Transformation | bar: 2026-06-01 to 2026-09-01
1. Ingestion Pipeline | bar: 2026-06-01 to 2026-07-01
2. Error Handling and Logging | bar: 2026-06-01 to 2026-07-01
3. Monitoring Alerts | bar: 2026-06-01 to 2026-07-01
4. Data Cleansing | bar: 2026-07-01 to 2026-08-01
5. Transformation Logic | bar: 2026-07-01 to 2026-08-01
6. Reconciliation Logic | bar: 2026-08-01 to 2026-09-01
7. Data Quality Exception Monitoring | bar: 2026-08-01 to 2026-09-01
8. Quarterly Data Load and Verification | bar: 2026-09-01
9. Cross-client Dataset Mapping and Testing | bar: 2026-09-01
4. Automation, Testing & Deployment | bar: 2026-09-01 to 2026-10-01
1. Journals Criteria and Workpapers | bar: 2026-09-01
2. Automated Routing of Workpapers | bar: 2026-09-01
3. Automated Scripts for Audit and Testing | bar: 2026-09-01
4. Risk Assessment Dashboards | bar: 2026-09-01
5. Refactoring Design | bar: 2026-10-01
5. Training & Process Documentation | bar: 2026-10-01
1. Documentation and Access Provisioning | bar: 2026-10-01
2. Training and Information Sessions | bar: 2026-10-01
3. Feedback and Refinements | bar: 2026-10-01
4. Usage Monitoring and Reporting | bar: 2026-10-01
5. Develop Business Process Documentation | bar: 2026-10-01